SalesVerse 2.0

Test Strategy

Test levels, environments, entry and exit criteria, defect management, tooling, traceability, schedule and the status of testing on the current build

IIFT Agent/Banca Portal & Back-office for Insurans Islam Family Takaful Sendirian Berhad

|  | PREPARED FOR Insurans Islam Family Takaful Sendirian Berhad Bandar Seri Begawan, Brunei Darussalam PREPARED BY iorta TechNXT https://iortatechnxt.com |
| --- | --- |

| Document reference | IIFT-SV2-TST |
| --- | --- |
| Version | 1.0 |
| Date | October 2026 |
| RFP deliverable | DEL-12 (Test Strategy); with the Test Cases workbook: DEL-13, DEL-14 precursor, DEL-15 basis |
| Status | Issued with the proposal |
| Classification | Commercial-in-Confidence |

Commercial-in-Confidence. Prepared by iorta TechNXT for Insurans Islam Family Takaful Sendirian Berhad as part of the response to IIFT's Request for Proposal for an Agent/Banca Portal and Back-office solution. Not to be disclosed to third parties without prior written consent.

# Document Control

This document defines how SalesVerse 2.0 is tested for IIFT: the test levels from unit tests to user acceptance, the environments and data, the criteria for entering and leaving each phase, how defects are classified and resolved, who does what, the tools, the traceability from RFP requirement to test case, the schedule within the 24-week plan, and the metrics reported. Its last chapter states the status of testing on the build submitted with the proposal, counted from the same data as the Test Cases workbook.

### Version history

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| 0.9 | September 2026 | iorta TechNXT | Internal technical review |
| 1.0 | October 2026 | iorta TechNXT | Issued with the tender proposal |

### Review and approval

| Role | Name | Signature / date |
| --- | --- | --- |
| Prepared by (Solution Architect, iorta TechNXT) | [Name] |  |
| Reviewed by (Engineering Lead, iorta TechNXT) | [Name] |  |
| Approved by (Project Director, iorta TechNXT) | [Name] |  |
| Accepted by (IIFT IT) | [Name, designation] |  |

### Document pack

| Reference | Document | RFP deliverable | Status |
| --- | --- | --- | --- |
| IIFT-SV2-SAD | SalesVerse 2.0 Solution Architecture | DEL-06 | Issued |
| IIFT-SV2-DD | SalesVerse 2.0 Data Dictionary | DEL-07 | Issued |
| IIFT-SV2-PSH | SalesVerse 2.0 Production Support Handover | DEL-26, DEL-27, MNT-28 | Issued |
| IIFT-SV2-CSQ | SalesVerse 2.0 Code Standards & Quality Report | DEL-11, NFR-14 | Issued |
| IIFT-SV2-SAR | SalesVerse 2.0 Security Assessment Report | DEL-17, NFR-13 | Issued |
| IIFT-SV2-TST | SalesVerse 2.0 Test Strategy | DEL-12 | This document |
| IIFT-SV2-TCS | SalesVerse 2.0 Test Cases | DEL-13, DEL-14 (precursor) | Issued |

### Related material

SalesVerse-2.0-Test-Cases.xlsx (IIFT-SV2-TCS): scenarios, conditions, cases, defects, traceability and the execution log; its Summary sheet and chapter 12 of this document are built from one source.

SalesVerse-2.0-Security-Assessment-Report: the OWASP checks referenced by the security cases.

SalesVerse-2.0-Code-Standards-and-Quality-Report: unit and end-to-end test evidence and coverage.

SalesVerse-2.0-Solution-Architecture: environments, integration adapters and deployment options.

### Conventions

Monetary amounts are in Brunei dollars (B$). Times are Brunei time (UTC+8) unless marked UTC.

RFP requirement identifiers (AP, BO, INT, COM, NFR, DEL, MNT) refer to IIFT's Request for Proposal. COM-01 to COM-10 in this pack are the shared platform requirements of RFP section 4.4.

Items marked delivered during implementation are designed here but not yet present in the working application; everything else describes the application as it runs today.

Option A, B and C are the commercial options of the proposal: on-premise with a perpetual licence, subscription hosted and managed by iorta on cloud, and source code handover. Prices and commercial terms are in the proposal and its pricing workbook; this pack quotes a figure only where a technical statement depends on it, and reads it from the same source as the proposal.

Text in [square brackets] is to be completed with IIFT during mobilisation.

# Contents

Right-click here and choose Update Field to build the table of contents.

# 1. Purpose and scope

This strategy covers the testing of SalesVerse 2.0 configured as the IIFT Agent/Banca Portal & Back-office: the Agent/Banca Portal, the Back-office, the public e-signature page, the system-to-system APIs and the integrations with IIFT's core, financial, AML, directory, e-mail and SMS services. It applies from the build sprints to hypercare and is the reference for the SIT and UAT deliverables (DEL-13 to DEL-16), the security assessment (DEL-17) and the performance report (DEL-18).

The companion workbook holds the test scenarios, conditions and cases with their current status. Both are generated from one catalogue in the source repository, so the counts in chapter 12 and in the workbook's Summary sheet cannot differ; the build stops if they do.

Out of scope: testing of IIFT's own systems beyond their interfaces, and of the hosting infrastructure other than through the availability, backup and DR drills in which iorta participates.

## 1.1 Test objectives

Prove every functional requirement of RFP sections 4.1 to 4.4 and the five product flows of Appendix 3 with at least one executed, passed case, traced in the workbook.

Prove the non-functional requirements of section 5 at the agreed level: security before any release, performance and availability at IIFT scale before go-live.

Find defects early: unit and API tests run with every change, business journeys on every release candidate, and the OWASP checks each sprint.

Give IIFT evidence it can audit: JSON results from every automated run, request and response summaries from the scripted API run, screen captures from manual runs, and signed UAT records.

# 2. Test levels and approach

Testing is layered. Each level has an owner, an environment, tooling and an exit criterion; the levels build on each other so that SIT and UAT concentrate on IIFT's systems, data and users rather than on application logic already proven.

Figure 1: Test levels across the delivery plan

| Level | Scope | Owner | Environment | Tooling | Exit criterion |
| --- | --- | --- | --- | --- | --- |
| Unit | Business rules, rating engines (all seven products), validators, password policy, encryption, file inspection, report export, web components and utilities | Developers | Developer workstation; CI on every push | Vitest (API), Vitest + Testing Library + jsdom (web) | All tests pass; coverage of core modules ≥ 70% |
| Integration / API | Every endpoint with positive and negative cases: permissions per role, audience separation, data scoping, validation, business-rule errors | Developers, QA | CI with PostgreSQL (dedicated *_test database rebuilt from the migrations) | Vitest + supertest | All tests pass; no endpoint without a negative test |
| End-to-end API (business journeys) | Quotation to e-Policy and e-Receipt, referral and maker-checker, onboarding with AML, claims, issues, reports, EOD and reconciliation, administration | QA | CI and the iorta test instance with demonstration data | Vitest e2e suite; tools/testing/api-test-run.mjs against a running instance | All journeys pass on the release candidate |
| UI / component | Web components, navigation, permission gating, forms; exploratory runs of every screen | QA | iorta test instance (browser) | Testing Library; Playwright smoke suite (regression); exploratory sessions with screen captures | No open Critical/High UI defects; smoke suite green |
| System integration test (SIT) | End-to-end flows across portal, back-office and IIFT systems: Core, FIN, AML service, Active Directory, SMTP relay, SMS gateway; scheduled jobs; EOD with FIN and BRR reconciliation | iorta QA with IITH system owners | SIT environment at IIFT with test endpoints and credentials | This workbook (cases marked SIT) plus the automated suites; Playwright regression | ≥ 95% of SIT cases passed; no open Critical/High defects; reconciliation MATCHED for three consecutive days |
| Performance | Load at 100 concurrent users, stress to the breaking point, 8-hour soak, five-year data volume | iorta performance engineer | Production-like SIT environment | k6 scenarios; Grafana/Prometheus | p95 < 2 s for normal transactions; error rate < 0.1%; no resource growth in the soak (DEL-18) |
| Security | SAST, secret scan, dependency audit and container scan in CI; OWASP Top 10 check script before each release; independent VAPT with re-test | iorta DevOps/QA; independent tester | CI; iorta test instance; IIFT UAT or production-like environment for the VAPT | CodeQL, gitleaks, npm audit, Trivy, security-checks.mjs; VAPT provider's tooling | No open Critical/High findings at go-live (DEL-17) |
| User acceptance (UAT) | Business scenarios per product (FFR01–FFR05) and per role, run by IIFT users; browser matrix on IIFT devices; accessibility basics | IIFT business users with iorta support | UAT environment with masked production data | UAT scripts derived from the scenarios marked UAT; defect log | Signed UAT certificate; no open Critical/High defects (DEL-15, DEL-16) |
| Regression | Automated suites and Playwright smoke re-run on every release candidate and every fix | QA | CI; SIT | Vitest, Playwright | 100% of critical paths automated and green before any deployment |
| Migration rehearsal | Two dry-runs of extraction, transformation, load and reconciliation | iorta, IIFT data owners | UAT | Migration scripts; reconciliation reports | 100% record count and control-total match |
| DR drill | Failover to the DR site/region and failback; restore from backup | IITH IT (Option A) or iorta managed services (Option B) with iorta support | DR site/region | Runbooks of the Production Support Handover | RTO ≤ 4 h, RPO ≤ 15 min achieved and documented (NFR-19) |
| Operational readiness | Deployment rehearsal, rollback, monitoring and alert rules, go-live checklist | iorta, IITH IT | Pre-production | Deployment plan; checklists (DEL-20, DEL-21) | Checklist complete; rollback rehearsed; hypercare entry criteria met |

Table 1: Test levels

## 2.1 Approach by type of requirement

Business rules and rating (Appendix 3, AP-19, AP-32): unit tests of the rating engines for all seven products with the indicative rates, then API cases that re-rate on submission; IIFT's approved rate tables are loaded in design and the expected contributions in the cases are refreshed with them.

Workflows and maker-checker (BO-16 to BO-19, COM-04): every approval type has cases for inbox visibility, segregation of duties, mandatory remarks, withdrawal and history.

Security (COM-01, COM-02, COM-10, NFR-08 to NFR-14): automated OWASP checks with every release, CI gates on every push, and the independent VAPT before go-live.

Integrations (INT-01 to INT-15): tested first against the simulated adapters (outbox, retry, dead letter, idempotent EOD postings, reconciliation), then in SIT against IIFT's test endpoints.

Scheduled jobs (expiry, grace period, EOD, SLA monitor, scheduled reports): logic tested through the API and the suites; schedules observed in SIT with jobs enabled.

Usability, browsers and accessibility (NFR-22 to NFR-24): exploratory runs at desktop and mobile widths now; browser matrix and accessibility checks with IIFT testers in UAT.

# 3. Test environments and data

| Environment | Provided by | Use | Data |
| --- | --- | --- | --- |
| DEV / CI | iorta | Build and unit, API and end-to-end tests on every push; dedicated PostgreSQL database named *_test, dropped and rebuilt from the migrations and seeds before each end-to-end run | Reference data and the demonstration data set (seed-demo.ts) |
| iorta test instance | iorta | Running instance with simulated integrations (INTEGRATION_MODE=simulated); used for the API run, the security checks and exploratory UI runs | Demonstration data set: three agencies, named demonstration users for every role, policies in every status, blocked bank, AML cases, issues |
| SIT | IIFT/IITH (Option A) or iorta cloud (Option B), available by week 8 | Live adapters to Core, FIN, AML, AD, SMTP and SMS test endpoints; jobs enabled; ClamAV; monitoring stack | Demonstration data plus IIFT test cases' data; migration dry-run output for the second cycle |
| UAT | IIFT, available by week 16 | Production configuration; the independent VAPT runs here | Masked copy of production data where available, otherwise the migrated data of dry-run 2; test accounts per role |
| Pre-production / performance | IIFT (SIT sized like production) | Performance and soak tests; deployment rehearsal | Five-year projected volume generated from the demonstration profile (Appendix 2) |

Table 2: Environments

## 3.1 Test data

The demonstration data set is generated through the application's own services (registration, screening, quotation, submission, payment, verification, issuance, renewal, endorsement, claims, issues, EOD, reconciliation), so every record carries a genuine history, audit trail and outbox messages.

Named demonstration users exist for every role; each case states which user it uses.

Scripted runs create their own records with a run identifier so they can be repeated; they never alter the seeded blocked bank or the demonstration passwords.

UAT uses masked production data where IIFT can provide it (identification numbers, contact details and names replaced); otherwise the migrated data of the second dry-run.

No production data is used outside IIFT's UAT and pre-production environments; the security check script and the API run must never be pointed at production.

# 4. Entry and exit criteria

| Phase | Entry criteria | Exit criteria |
| --- | --- | --- |
| Unit and API (CI) | Code reviewed; migrations applied cleanly | All tests pass; lint, type check and format clean; coverage ≥ 70% on core modules; no Critical/High dependency findings |
| End-to-end and release candidate | CI green; release notes drafted; demonstration data loaded | End-to-end suite and API run green; OWASP checks 29/29; Playwright smoke green; test cases workbook refreshed |
| SIT | Release candidate deployed to SIT; interfaces, test endpoints and credentials available (week 8 assumption); SIT cases reviewed with IITH owners; test data prepared | ≥ 95% cases passed, 100% of Must requirements covered; no open Critical/High; Medium defects with agreed workaround or fix date; reconciliation MATCHED three days running; SIT results report (DEL-14) issued |
| Performance | SIT functional exit; production-like sizing; monitoring in place | Targets met or deviations accepted by IIFT with a remediation plan; report issued (DEL-18) |
| Security (VAPT) | SIT functional exit; rules of engagement signed; test accounts per role | No open Critical/High; Medium/Low with dates; re-test report issued (DEL-17) |
| UAT | SIT exit; UAT environment with masked data; testers trained; UAT scripts approved | All UAT scripts executed; no open Critical/High; signed UAT certificate (DEL-16) |
| Go-live | UAT sign-off; VAPT cleared; migration dry-run 2 reconciled; DR drill done; go-live checklist complete (DEL-21) | Production deployment verified by the smoke checklist; hypercare entry |

Table 3: Entry and exit criteria per phase

Exit decisions are taken by the test manager with IIFT's product owner at the phase review; deviations (for example a Medium defect deferred) are recorded in the phase report with the agreed date.

# 5. Defect management

Defects are logged with steps, data, expected and actual result, evidence and the case identifier; they are triaged daily during SIT and UAT. Severity describes the impact, priority the urgency of the fix. A fixed defect is re-tested by the person who found it where possible, and the related automated cases are extended so that the defect cannot return unnoticed.

| Severity | Definition | Resolution target |
| --- | --- | --- |
| Critical | System unusable, data integrity or security at risk, or a Must requirement cannot be met; no workaround | Fix before exit of the current phase; in production, P1 handling (contained within 24 h) |
| High | Key function fails or gives wrong results; workaround difficult | Fix before exit of the current phase; in production, 14 days |
| Medium | Function impaired with an acceptable workaround | Fix before go-live or agreed deferral with IIFT |
| Low | Cosmetic, wording or minor usability | Planned release |

Table 4: Defect severity

| Priority | Definition | Target |
| --- | --- | --- |
| Urgent | Blocks testing of other cases or a milestone | Next build (within 1 working day in SIT/UAT) |
| High | Needed for the current phase exit | Within 3 working days |
| Medium | Needed before go-live | Next planned build |
| Low | Improvement; can follow go-live | Backlog |

Table 5: Defect priority

## 5.1 Defect workflow

Steps

| # | Action |
| --- | --- |
| 1 | Log the defect in the agreed tool with the case identifier, environment, build and evidence. |
| 2 | Triage (daily): confirm, set severity and priority, assign to iorta; reject duplicates or expected behaviour with a note. |
| 3 | Fix and unit-test; add or extend an automated case; deliver in the next build with release notes. |
| 4 | Re-test the case and the related regression set; close or re-open with evidence. |
| 5 | Report open defects by severity and age in the daily and weekly reports; agree deferrals with IIFT. |

# 6. Roles and responsibilities

| Role | Responsibilities |
| --- | --- |
| Test manager (iorta) | Owns this strategy, the workbook, entry/exit decisions, defect triage, reporting |
| QA engineers (iorta) | Write and run cases, maintain the automated suites and the API run script, record evidence, re-test fixes |
| Developers (iorta) | Unit and API tests with every change; fix defects; support SIT and UAT |
| DevOps and security engineer (iorta) | CI gates, environments, performance tests, VAPT coordination and remediation tracking |
| Business analyst (iorta) | Scenario review against the BRS/FRS and Appendix 3 flows; UAT script preparation and support |
| IIFT UAT testers / super-users | Execute UAT scripts, record results and defects, confirm business acceptance; browser checks on IIFT devices |
| IIFT product and business owners | Approve UAT scripts and exit; decide on deferrals; sign the UAT certificate |
| IITH IT | SIT and UAT environments, interface test endpoints and credentials, AD, SMTP, SMS, monitoring, backup/DR drills; participation in SIT of interfaces |
| Independent VAPT provider | Vulnerability assessment and penetration test, re-test, report |

Table 6: Roles

# 7. Tooling

| Tool | Use |
| --- | --- |
| Vitest | Unit and API/end-to-end test runner (JSON reports kept as evidence) |
| supertest | HTTP calls against the application in the end-to-end suite |
| Testing Library + jsdom | Web component tests |
| Playwright | Browser smoke and regression suite (SIT onwards) |
| tools/testing/api-test-run.mjs | Scripted system cases against a running instance; writes evidence/api-test-run.json |
| tools/security/security-checks.mjs | 29 OWASP Top 10 checks; evidence/security-checks.json |
| CodeQL, gitleaks, npm audit, Trivy, CycloneDX SBOM | CI security gates |
| k6, Grafana, Prometheus | Performance scenarios and measurements |
| Issues module / IIFT's defect tool | Defect log during SIT and UAT (IIFT's tool if preferred; export to the SIT and UAT results reports) |
| docs/technical/build | Generates this strategy and the workbook from the catalogue and the evidence files |

Table 7: Tools

Every automated run writes a JSON report that is kept under docs/technical/evidence and read when the workbook and this document are rebuilt, so the recorded status is always the result of a real run, never a typed value.

# 8. Traceability

Traceability runs from the RFP requirement to the executed case in four links, all held in the workbook:

| Link | Artefact | Identifier | Content |
| --- | --- | --- | --- |
| 1 | RFP requirement | AP-nn, BO-nn, INT-nn, COM-nn, NFR-nn, DEL-nn, MNT-nn, FFR0n | Requirement and short title (Traceability sheet) |
| 2 | Test scenario | TS-nn | Business or technical situation, persona, pre-conditions, expected end state, RFP identifiers covered |
| 3 | Test condition | TC-nnn | One rule or decision inside the scenario that must be verified |
| 4 | Test case | CS-nnnn | Steps, data, expected result, level, automation, status, evidence, execution details, defect reference |

Table 8: Traceability links

The Traceability sheet shows, for each requirement, the scenarios, the case identifiers and a coverage status (executed – passed, partly executed, cases defined but not executed, no case yet). The build fails if a scenario cites an unknown requirement, if a condition has no case, or if a case cites evidence that does not exist. UAT scripts (DEL-15) are produced from the scenarios whose persona is an IIFT user, with the business language of Appendix 3.

| Catalogue element | Count |
| --- | --- |
| Functional and technical areas | 22 |
| Test scenarios | 70 |
| Test conditions | 196 |
| Test cases | 438 |
| RFP requirements traced | 169 |

Table 9: Catalogue size

# 9. Schedule

The schedule follows the 24-week delivery plan of the proposal: SIT, performance and VAPT in weeks 16 to 19, UAT in weeks 19 to 22, go-live in week 24 and 4 weeks of hypercare.

| Weeks | Activity | Testing | Output / milestone |
| --- | --- | --- | --- |
| 6–16 | Build sprints | Unit, API and end-to-end tests with every story; sprint demo acceptance; OWASP checks each sprint | CI green per sprint |
| 16 | Hardening | Full regression; API run; security checks; workbook refreshed; SIT readiness review | Build complete (M3) |
| 16–19 | SIT | SIT cases with IITH interface owners; three EOD/reconciliation cycles; defect fixing and re-test | SIT results (DEL-14) |
| 17–18 | Performance | Load, stress, soak and volume tests; tuning | Performance report (DEL-18) |
| 17–19 | VAPT | Independent test, remediation, re-test | Security assessment (DEL-17); SIT exit and security clearance (M4, week 19) |
| 19–22 | UAT | IIFT testers execute UAT scripts; daily triage; browser matrix; accessibility checks | UAT results and sign-off (DEL-16, M5 week 22) |
| 19–23 | Migration rehearsals | Dry-run 1 and 2 with reconciliation | Migration plan and reconciliation reports |
| 23 | Readiness | Deployment rehearsal, DR drill, go-live checklist | Go/no-go (DEL-21) |
| 24 | Go-live | Production smoke checklist; first EOD monitored | Production deployment (DEL-28, M6) |
| 25–28 | Hypercare | Daily checks; fixes under warranty; regression before each patch | Hypercare exit (M7) |

Table 10: Test schedule

# 10. Metrics and reporting

| Metric | Definition | Frequency |
| --- | --- | --- |
| Execution progress | Cases planned, executed, passed, failed, blocked per level and per area | Daily in SIT/UAT; weekly to the Working Committee |
| Pass rate | Passed / executed; target ≥ 95% at SIT exit, 100% of Must requirements | Daily / weekly |
| Requirement coverage | RFP requirements with at least one executed and passed case (Traceability sheet) | Weekly; 100% at UAT exit |
| Defects | Open by severity and age; found vs fixed per week; re-open rate | Daily / weekly |
| Automation | Share of cases automated; regression duration | Per release |
| Non-functional | p95 response time, error rate, throughput, resource use | Performance report |
| Security | Findings by severity and remediation status | VAPT report and re-test |

Table 11: Metrics

Daily SIT/UAT report: cases executed and passed, blockers, defects found and fixed, open by severity.

Weekly Working Committee report: progress against plan, pass rate, coverage, defect trend, risks.

Phase reports: SIT results (DEL-14), performance report (DEL-18), security assessment and VAPT re-test (DEL-17), UAT results and certificate (DEL-16); each attaches the workbook refreshed on that date.

# 11. Risks and mitigations

| Risk | Effect | Mitigation |
| --- | --- | --- |
| Interface test endpoints or credentials late (Core, FIN, AML, AD) | SIT slips | Simulated adapters allow all flows to be tested first; interface cases isolated and scheduled last; dependency tracked from week 8 |
| Shared demonstration accounts used by several testers | Sessions ended by the single-active-session rule; misleading failures | Named accounts per tester in SIT/UAT; the API run re-signs in and records it |
| Time-zone-dependent tests and jobs | Flaky results near midnight Brunei time | All tests use the business-day helper (DEF-001); jobs tested at their scheduled time in SIT |
| UAT tester availability | UAT exceeds weeks 19–22 | Testers named by week 16; scripts short and per role; iorta on site |
| Performance environment not production-like | Results not representative | Sizing agreed in the Solution Architecture; environment checked before the test; results reported with configuration |
| VAPT findings late in the plan | Go-live at risk | Internal checks and CI gates first; VAPT starts at SIT functional exit; remediation window reserved in week 19 |
| Migration data quality | Reconciliation mismatches | Two dry-runs; corrections at source; exception reports |

Table 12: Test risks

# 12. Status post testing

Status of testing on the build of 2 October 2026 (source commit d161514), counted from the evidence files listed in the annex. The figures are the same as on the Summary sheet of the Test Cases workbook; the build of this pack verifies that they agree.

| Status | Cases | Share | Meaning |
| --- | --- | --- | --- |
| Passed | 384 | 88% | Executed with the expected result (automated suites, API run, security checks, manual runs with screen captures) |
| Failed | 2 | 0% | Executed; expected result not observed; defect logged |
| Blocked | 1 | 0% | Pre-condition not available in the test data at the time of the run |
| Not executed | 51 | 12% | Needs IIFT's environment, scale, users or a time-based job; reason stated per case |
| Total | 438 | 100% | 70 scenarios, 196 conditions |

Table 13: Cases by status

| Level | Cases | Passed | Failed | Blocked | Not executed |
| --- | --- | --- | --- | --- | --- |
| Unit (API and web components) | 150 | 150 | 0 | 0 | 0 |
| API system cases executed against the running system | 122 | 111 | 1 | 1 | 9 |
| End-to-end API suite (business journeys) | 44 | 43 | 1 | 0 | 0 |
| User interface (manual, exploratory) | 57 | 51 | 0 | 0 | 6 |
| Security checks (OWASP Top 10) | 34 | 29 | 0 | 0 | 5 |
| System integration test with IIFT systems | 25 | 0 | 0 | 0 | 25 |
| Performance | 3 | 0 | 0 | 0 | 3 |
| User acceptance | 3 | 0 | 0 | 0 | 3 |

Table 14: Cases by level

| Automation | Cases |
| --- | --- |
| Automated | 223 |
| Executed – API run | 113 |
| Manual | 51 |
| Not automated | 51 |

Table 15: Cases by automation

## 12.1 What was executed

Unit tests: 59 of 59 API tests and 91 of 91 web tests passed in the re-run of 2 October 2026.

End-to-end suite: 31 of 32 journeys passed in the re-run; all 32 passed in the earlier evidence run of the same day (see DEF-001).

API run: 111 of 113 system cases passed against the running demonstration instance (http://localhost:3000), executed by iorta TechNXT QA (API run) on 2026-10-02 starting 22:12 UTC; every request and response is in the Execution log sheet.

Security: 29 of 29 OWASP checks passed (2 October 2026, 14:57 UTC); details in the Security Assessment Report.

Manual exploratory runs of the portal and back-office screens with screen captures held in evidence/ui-screens.

## 12.2 Defects

| ID | Title | Severity | Status |
| --- | --- | --- | --- |
| DEF-001 | End-to-end claim test uses the UTC calendar day instead of the Brunei business day | Low | Open – fix in test code (use the business-day helper); no product change |
| DEF-002 | Administrator password reset re-activates a disabled account | Medium | Open – fix proposed: keep the status on reset and audit any re-activation; to be confirmed with IIFT |

Table 16: Defects found

DEF-001 – The test 'accepts claim notifications only within the period of cover' notifies a claim dated today() in UTC. Policies seeded after 16:00 UTC start on the next Brunei day, so the claim is refused with CLAIM_NOT_VALID and the test fails when the suite runs between 16:00 and 24:00 UTC. The application behaves correctly (the same case passed in the API run with the Brunei date, EX-067). The evidence run at 14:50 UTC passed; the re-run at 22:00 UTC failed.

DEF-002 – Resetting the password of a user whose status is DISABLED sets the status back to ACTIVE, and the user can sign in with the temporary password (EX-134: reset 200, sign-in 200). The audit trail records USER_PASSWORD_RESET only, not a re-activation. An administrator who resets a password should not silently re-enable an account that another administrator disabled; re-activation should be an explicit, separately audited status change (BO-03, NFR-10). The unlock function behaves correctly (it refuses disabled accounts).

## 12.3 Not executed and why

| Reason | Cases | Cases concerned |
| --- | --- | --- |
| Requires IIFT environment | 21 | Application instance and database failover; Back-office sign-on through IIFT Active Directory; Backup and restore drill; Browser matrix on IIFT devices; Core and FIN live delivery; DR failover drill; Deployment rehearsal and rollback; E-mail and SMS delivery through IIFT gateways; External AML service screening; Independent VAPT and re-test; Load test: p95 response time at 100 concurrent users; Mi |
| Other | 11 | CI security gates; Dead-letter alert e-mail; Grace-period job blocks and unblocks an agency; LDAP filter escaping; Malware scan refuses an infected upload; Manual lift of a payment block; OWASP check script before release; Overseas Student Tertiary plan; Property financing with profit basis NONE; Retention and archival policy; Sign-in rate limit per client address |
| Scheduled for SIT regression | 9 | Atomic issuance under failure; Cancellation approved sets CANCELLED; Document expiry warning; Expired quotation cannot be submitted; Expiry job and renewal notices; Optimistic locking on concurrent edits; Password history and expiry; Rates re-applied at submission after a rate change; Second approval level above B$300,000 |
| UI under restyling at the time of the run | 6 | Accessibility review; Agent search filters; Attachments on issues; Billing figures reconcile with the policy list; Khairat renewal unavailable in the portal UI; Participant search in the back-office |
| Time-based job or timeout | 3 | Absolute timeout ends the session after 8 hours; Idle timeout ends the session after 15 minutes; Scheduled EOD at 23:30 Brunei time |
| Not yet built | 1 | Back-office MFA |

Table 17: Cases not executed in the iorta test environment

Reading the status Everything that can be proven on the application alone has been executed. Two cases failed: the end-to-end claim test affected by DEF-001 (a test-code issue) and the password-reset case that found DEF-002 (a disabled account is re-activated by a reset). One renewal case was blocked by exhausted test data. What remains needs IIFT's interfaces, scale, devices or users, or a scheduled job observed at its time, and is planned for SIT, performance testing, VAPT and UAT in weeks 16 to 22. During the first API run on 2 October 2026, other engineers signed in to the shared demonstration accounts from the user interface; the single-active-session rule ended the run's sessions. The script now signs in again when that happens and the run was repeated; the recorded run is the final one.

# Annex – Evidence files

Results in this report are read from the evidence files below when the report is built. The fingerprint is the start of each file's SHA-256 hash, so a reader can confirm which evidence a given version of the report was built from.

| Evidence file | Size | SHA-256 (first 16 characters) |
| --- | --- | --- |
| api-e2e-coverage-summary.json | 42,784 bytes | 74b2c247a495d346… |
| api-e2e-tests.json | 895,673 bytes | bb1381c4fef07679… |
| api-static-analysis.json | 796 bytes | 38c06cf62d020977… |
| api-test-run.json | 62,933 bytes | bf46e22aaf170745… |
| api-unit-coverage-summary.json | 41,871 bytes | 501662d3899973ad… |
| api-unit-tests.json | 901,653 bytes | 04b9d616f28c707b… |
| code-metrics-api.json | 760 bytes | ec37c59d47c8708c… |
| npm-audit.json | 366 bytes | 1cf279e9ef691d09… |
| runtime-dependency-licences.json | 40,391 bytes | b003a0dc1a75e06f… |
| security-checks.json | 9,685 bytes | 5ab9bdeea3c926fd… |
| test-reruns.json | 40,047 bytes | 99a7e747f67f05b0… |
| web-build.txt | 9,886 bytes | 78590222981eafd9… |
| web-lint.json | 197 bytes | 21a8be1488eb17d7… |
| web-typecheck.txt | 26 bytes | e5073c15448438bb… |
| web-unit-tests.json | 24,628 bytes | 7dac851fc00c909f… |

Table 18: Evidence files